## 08102018-14102018
Last week | STT | Work | Percent (%)
| 1 | Báo cáo proposal | 60
Problems | STT | Content
This week | STT | Work | Percent (%)
| 1 | Khảo sát phần mềm | 100
| 2 | vẽ use case | 100
| 3 | Vẽ activity diagram | 100
| 4 | báo cáo proposal | 40

## 15102018-21102018
This week | STT | Work | Percent (%)
| 1 | Khảo sát phần mềm | 100
| 2 | vẽ use case | 100
| 3 | Vẽ activity diagram | 100
| 4 | báo cáo proposal | 40
Problems | STT | Content
| 1 | Có một số thành viên chưa nắm rõ UML nên lúc làm có hơi khó khăn và sai sót
This week | STT | Work | Percent (%)
| 1 | Báo cáo Yêu cầu phần mềm | 100
| 2 | Design database, class diagram | 100
| 3 | Design giao diện: - Trang chủ - Main menu (menu left), contain menu of user | 100
| 4 | Design giao diện: - Restaurant list (total list, marklist, recent list) | 100
| 5 | Design giao diện: - Restaurant detail (contain info, event, comment) | 100
| 6 | Design giao diện: - Dish detail (info, comment - having comment form) | 100
| 7 | Design giao diện: - Login and Register form | 100
| 8 | Design giao diện: - Manage menu, having screens: show menu, add dish, update dish, delete dish (design popup menu for item) | 100
| 9 | Design giao diện: - Manage event, having screens: show event list, add event, update event, delete event (design popup menu for item) | 100
| 10 | Design giao diện: - Manage account, contain screens: show profile, update profile for customer and restaurant, change password | 100
| 11 | Design giao diện: - Manage mark, contain screens: show marks, delete mark | 100