## Plan of ConvenientMenu
|  |  | Total | 9 tuần
Person | Task | Content | Start
All | 1 | Phân tích use case, activity diagram | 1 tuần (6)
All | 2 | * Design UI: + trang chủ: haveing high rating restaurant, new event (of all restaurant), high rating dish + Menu main for direct to: restaurant list, search dish (total) + view restaurants list (have searching form for restaurant): total list, mark list (if login), recent list (Những nhà hàng đã xem gần đây) + view restaurant detail: menu (dish list), event list, comment list (have form for commenting) + view dish detail: information, comment (having form for commenting) + menu for user and restaurant: having buttons: avatar, login, register, profile, logout (common). Special: manage menu, manage event (restaurant), manage mark (user) + login and register form for user and restaurant + magage menu of restaurant: home manage (show list of dish (follow type) of restautant), Add dish form, Update dish form, delete dish + manage event of restaurant: home manage (show list of event of restaurant), Add event form, Update event form, delete event + searching form: for total, restaurant and dish (total and special). + manage account: show profile, update profile for user and restaurant, change pasword form, confirm change password + popup menu for each item (restaurant of dish). + Manage mark: show mark, delete mark, popup menu for mark item * Design process: Others interface user and interface functionality for process * Design Database, class diagram | 1 tuần (7)
Tứ | 3 | Code interface and functionality for home page | 1 tuần (8)
Tư | 4 | Code interface and functionality for menu main | 1 tuần (8)
Tứ, Tú | 5 | Code interface and functionality for view dish detail | 1 tuần (8)
Thanh, Việt | 6 | Code interface and functionality for view restaurant detail | 1 tuần (8)
Việt, Tư | 7 | Code interface and functionality for restaurant list | 1 tuần (8)
Việt | 8 | Code interface and functionaltity for login, register for restaurant (all case can occur) | 2 tuần (9,10)
Tứ, Tư | 9 | Code interface and functionality for manage menu for restaurant (having popup menu for delete item) | 2 tuần (9,10)
Thanh, Tú | 10 | Code interface and functionality for manage event for restaurant (having popup menu for delete item) | 2 tuần (9,10)
Việt | 11 | Code functionality for comment function | 2 tuần (9,10)
Việt | 12 | Code functionality for searching | 1 tuần (11)
Tú | 13 | Code interface and functionality for direction menu for user and restaurant | 1 tuần (11)
Tư | 14 | Code interface and functionality for manage profile | 1 tuần (11)
Thanh | 15 | Code interface and functionality for change password | 1 tuần (11)
Tứ | 16 | Code interface and functionality mark for user | 1 tuần (12)
|  | Test | 1 tuần (12)

## Gantt chart
Tasks
Start Date | End Date | Description | Duration (days) | Dependencies
2018-10-08 | 2018-10-14 | Task 01 | 7
2018-10-15 | 2018-10-21 | Task 02 | 7
2018-10-22 | 2018-10-28 | Task 03 | 7
2018-10-22 | 2018-10-28 | Task 04 | 7
2018-10-22 | 2018-10-28 | Task 05 | 7
2018-10-22 | 2018-10-28 | Task 06 | 7
2018-10-22 | 2018-10-28 | Task 07 | 7 | M1
2018-10-29 | 2018-11-11 | Task 08 | 14 | T7
2018-10-29 | 2018-11-11 | Task 09 | 14 | T7
2018-10-29 | 2018-11-11 | Task 10 | 14 | T7
2018-10-29 | 2018-11-11 | Task 11 | 14 | T7(M2)
2018-11-12 | 2018-11-18 | Task 12 | 7 | T11
2018-11-12 | 2018-11-18 | Task 13 | 7 | T11
2018-11-12 | 2018-11-18 | Task 14 | 7 | T11
2018-11-12 | 2018-11-18 | Task 15 | 7 | T11
2018-11-19 | 2018-11-25 | Task 16 | 7 | T11(M3)